## Risk Register
Risk ID | Asset | Threat | Vulnerability | Risk Description | Likelihood (1-5) | Impact (1-5) | Risk Score | Risk Level | Risk Owner | Existing Controls | Recommended Controls | Residual Risk | Status
R-001 | Customer Database | Data Breach | Weak access control | Unauthorized access to sensitive customer data | 4 | 5 |  |  | CISO | RBAC, Firewall | Implement MFA, access reviews | Medium | Open
R-002 | Web Application | SQL Injection | Poor input validation | Injection attack to access DB | 3 | 5 |  |  | AppSec Lead | WAF | SAST/DAST | Medium | In Progress
R-003 | Employee Laptops | Malware | No endpoint detection | Malware infection risk | 4 | 4 |  |  | IT Head | Antivirus | Deploy EDR | Medium | Open

## Instructions
Cyber Security Risk Register Instructions
1. Enter Risk ID, Asset, Threat, Vulnerability, Description.
2. Provide Likelihood and Impact (1–5). Risk Score auto-calculates.
3. Risk Level is derived automatically.
4. Update controls and assign owner.
5. Track status regularly.